## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Bharkavi PM | 2026-07-23 | AST analyzer incorrectly calculated complexity for nested functions | Sprint 3 | Bharkavi PM | Maintainability | Updated AST visitor and complexity calculation logic | 2026-07-10 | Closed | Verified successfully
2 | Bharkavi PM | 2026-07-23 | Severity classification inconsistent in analyzers | Sprint 4 | Bharkavi PM | Logical | Added centralized severity mapping | 2026-07-23 | Closed | Standardized severity levels
3 | Bharkavi PM | 2026-07-23 | Inconsistent across multiple agents | Sprint 3 | Bharkavi PM | Standards | Implemented Findings Deduplicator module Agents | 2026-07-20 | Closed | Duplicate issues removed
4 | Bharkavi PM | 2026-07-23 | Analysis API response format inconsistent | Sprint 4 | Bharkavi PM | Maintainability | Standardized unified findings response model | 2026-07-23 | Closed | API validated
5 | Bharkavi PM |  |  | Sprint 5 | Bharkavi PM | Logical | Implemented AI Multi-Agent architecture | 2026-07-24 | Closed | Validated Success
6 | Bharkavi PM |  |  | Sprint 6 | Bharkavi PM | Logical | Security Analysis Agent | 2026-07-25 | Closed | Implemented Success
7 | Bharkavi PM |  |  | Sprint 7 | Bharkavi PM | User Interface | Streamlit Dashboard | 2026-07-28 | Closed | Easy level UI
8 | Bharkavi PM |  |  | Sprint 8 | Bharkavi PM | Maintainability | Remediation Agent | 2026-07-31 | Closed | Agents orchestra added
9 | Bharkavi PM |  |  | Sprint 9 | Bharkavi PM | Maintainability | Summary Agent | 2026-08-01 | Closed | Verfied
10 | Bharkavi PM |  |  | Sprint 10 | Bharkavi PM | Logical | AI Assistant | 2026-08-02 | Closed | RAG Assistant added
11 | Bharkavi PM |  |  | Sprint 11 | Bharkavi PM | User Interface | Streamlit Dashboard and remove duplicate knowledge base | 2026-08-03 | Closed | Easily accessible UI
12 | Bharkavi PM |  |  | Sprint 12 | Bharkavi PM | User Interface | Update Streamlit Dashboard | 2026-08-05 | Closed | Standardized UI

## Sheet2
Logical
User Interface
Maintainability
Standards
Others