## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Bharkavi PM | 2026-07-23 | AST analyzer incorrectly calculated complexity for nested functions | Sprint 3 | Bharkavi PM | Maintainability | Updated AST visitor and complexity calculation logic | 2026-07-10 | Closed | Verified successfully
2 | Bharkavi PM | 2026-07-23 | Severity classification inconsistent in analyzers | Sprint 4 | Bharkavi PM | Logical | Added centralized severity mapping | 2026-07-23 | Closed | Standardized severity levels
3 | Bharkavi PM | 2026-07-23 | Inconsistent across multiple agents | Sprint 3 | Bharkavi PM | Standards | Implemented Findings Deduplicator module Agents | 2026-07-20 | Closed | Duplicate issues removed
4 | Bharkavi PM | 2026-07-23 | Analysis API response format inconsistent | Sprint 4 | Bharkavi PM | Maintainability | Standardized unified findings response model | 2026-07-23 | Closed | API validated
5 | Bharkavi PM | 2026-07-23 | Severity classification inconsistency | Sprint 5 | Bharkavi PM | Logical | Implemented AI Multi-Agent architecture | 2026-07-24 | Closed | Validated Success
6 | Bharkavi PM | 2026-07-23 | Security agent rule tuning | Sprint 6 | Bharkavi PM | Logical | Security Analysis Agent | 2026-07-25 | Closed | Implemented Success
7 | Bharkavi PM | 2026-07-25 | Dashboard - UI | Sprint 7 | Bharkavi PM | User Interface | Streamlit Dashboard | 2026-07-28 | Closed | Easy level UI
8 | Bharkavi PM | 2026-07-25 | Multi-agent orchestration issue | Sprint 8 | Bharkavi PM | Maintainability | Remediation Agent | 2026-07-31 | Closed | Agents orchestra added
9 | Bharkavi PM | 2026-08-01 | Multi-agent orchestration issue | Sprint 9 | Bharkavi PM | Maintainability | Summary Agent | 2026-08-01 | Closed | Verfied
10 | Bharkavi PM | 2026-08-04 | RAG Agent development | Sprint 10 | Bharkavi PM | Logical | AI Assistant | 2026-08-02 | Closed | RAG Assistant added
11 | Bharkavi PM | 2026-08-05 | UI | Sprint 11 | Bharkavi PM | User Interface | Streamlit Dashboard and remove duplicate knowledge base | 2026-08-03 | Closed | Easily accessible UI
12 | Bharkavi PM | 2026-08-05 | UI Issue solve | Sprint 12 | Bharkavi PM | User Interface | Update Streamlit Dashboard | 2026-08-05 | Closed | Standardized UI
13 | Bharkavi PM | 2026-08-06 | Security Agent missed SQL Injection pattern in specific Python code | Sprint 7 | Bharkavi PM | Security | Updated OWASP rule mappings and detection patterns | 2026-08-06 | Closed | Verified
14 | Bharkavi PM | 2026-08-07 | Remediation Agent generated incomplete code fixes | Sprint 8 | Bharkavi PM | Logical | Added validation and fix verification workflow | 2026-08-07 | Closed | Verified
15 | Bharkavi PM | 2026-08-08 | Duplicate vectors generated during document ingestion | Sprint 9 | Bharkavi PM | Data | Added document hash validation | 2026-08-08 | Closed | Verified
16 | Bharkavi PM | 2026-08-09 | ChromaDB retrieval returned irrelevant chunks | Sprint 10 | Bharkavi PM | Performance | Improved chunking strategy and similarity search | 2026-08-09 | Closed | Verified
17 | Bharkavi PM | 2026-08-10 | LangGraph workflow execution sequence inconsistent | Sprint 11 | Bharkavi PM | Logical | Added workflow state management | 2026-08-10 | Closed | Verified
18 | Bharkavi PM | 2026-08-11 | Upload API timeout on large repositories | Sprint 12 | Bharkavi PM | Performance | Optimized repository scanning service | 2026-08-11 | Closed | Verified
19 | Bharkavi PM | 2026-08-12 | Chat Assistant hallucinated unsupported security recommendations | Sprint 13 | Bharkavi PM | AI Quality | Restricted responses using RAG context | 2026-08-12 | Closed | Verified
20 | Bharkavi PM | 2026-08-13 | Streamlit dashboard refresh issue after report generation | Sprint 14 | Bharkavi PM | UI | Added session state management | 2026-08-13 | Closed | Verified
21 | Bharkavi PM | 2026-08-14 | Report export failed for large findings lists | Sprint 15 | Bharkavi PM | Functional | Optimized report generator service | 2026-08-14 | Closed | Verified
22 | Bharkavi PM | 2026-08-15 | PostgreSQL transaction rollback issue during project deletion | Sprint 16 | Bharkavi PM | Database | Added transaction handling and exception management | 2026-08-15 | Closed | Verified

## Sheet2
Logical
User Interface
Maintainability
Standards
Others